## Worksheet
Phase |  |  |  | Task responsibility |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
| Module |  |  |  | Involved in creation of outcome
Task
Outcome
INITIATION
Project steering
|  | Decide on project release |  | Project sponsor
|  |  | Checklist |  | Project sponsor, Project manager
|  |  | Project order |  | Project sponsor, Project manager, Business process owner
|  |  | Project decision steering |  | Project sponsor, Project manager, Project committee member, Quality and risk manager
|  | Commission and steer initiation |  | Project sponsor
|  |  | Project initiation order |  | Project sponsor, Project manager
Project management
|  | Decide on an option |  | Project manager
|  |  | Checklist |  | Project manager
|  |  | Project decision management & execution |  | Project manager, Quality and risk manager
|  | Manage and control initiation |  | Project manager
|  |  | Work order |  | Project manager
|  |  | Project status report |  | Project manager
|  |  | Minutes |  | Project manager
|  |  | Stakeholder list |  | Project manager, Project sponsor, Business analyst, Business process owner
|  |  | Stakeholder Interests |  | Project manager
|  | Draw up project order |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Project order |  | Project manager, Business process owner
Project foundations
|  | Analyze the legal basis |  | Project manager
|  |  | Legal basis analysis |  | Project manager, Business process owner
|  | Analyze protection needs |  | ISDP manager
|  |  | Protection needs analysis |  | ISDP manager, Project manager, Business process owner
|  | Conduct a study |  | Project manager
|  |  | Study |  | Project manager, Business analyst, User representative, Business process owner, IT-architect
CONCEPT
Project steering
|  | Decide on phase release |  | Project sponsor
|  |  | Checklist |  | Project sponsor, Project manager
|  |  | QA and risk report |  | Project sponsor, Quality and risk manager
|  |  | Project decision steering |  | Project sponsor, Project manager, Project committee member, Quality and risk manager
|  | Steer project |  | Project sponsor
|  |  | QA and risk report |  | Project sponsor, Quality and risk manager
|  |  | Project decision steering |  | Project sponsor, Project manager, Project committee member, Quality and risk manager
Project management
|  | Lead change management |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Change request |  | Project manager, Business analyst, User representative
|  |  | Change status list |  | Project manager
|  | Agree on and steer goods/services |  | Project manager
|  |  | Quote request |  | Project manager
|  |  | Evaluation report |  | Project manager
|  |  | Agreement |  | Project manager, Project sponsor
|  | Prepare phase release |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Project status report |  | Project manager
|  |  | Phase report |  | Project manager
|  | Deal with problems and benefit from experience |  | Project manager
|  |  | Lessons learned |  | Project manager
|  | Manage and control project |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Work order |  | Project manager
|  |  | Project status report |  | Project manager
|  |  | Minutes |  | Project manager
|  | Perform quality assurance |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Review report |  | Project manager
|  | Manage risks |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Project status report |  | Project manager
|  | Manage stakeholders and communication |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Stakeholder list |  | Project manager, Project sponsor, Business analyst, Business process owner
|  |  | Stakeholder Interests |  | Project manager
Agile development
|  | Decide on agile development using SCRUM |  | Project manager
|  |  | Checklist |  | Project manager
|  |  | Project decision management & execution |  | Project manager, Quality and risk manager
|  | Keep a product backlog |  | Project manager
|  |  | Product backlog |  | Project manager, Business analyst, Developer
|  | Design release plan |  | Developer
|  |  | Release plan |  | Developer, Operations manager, Business analyst
|  | Introduce SCRUM |  | Project manager
|  |  | Project management plan |  | Project manager
|  | Conduct sprints |  | Developer
|  |  | Sprint backlog |  | Developer, Business analyst
|  |  | Increment |  | Developer
|  |  | Minutes |  | Developer, Project manager
Business organization
|  | Draw up business organization concept |  | Business analyst
|  |  | Business organization concept |  | Business analyst, User representative, Business process owner
IT system
|  | Decide on system architecture |  | Project manager
|  |  | Checklist |  | Project manager
|  |  | Project decision management & execution |  | Project manager, Quality and risk manager
|  | Design an integration concept |  | IT-architect
|  |  | Integration concept |  | IT-architect, Operations manager, Business analyst, Developer
|  | Realize prototype |  | Developer
|  |  | Prototype realized |  | Developer, IT-architect
|  |  | Prototype documentation |  | Developer, IT-architect
|  | Design a system concept |  | IT-architect
|  |  | Situation analysis |  | IT-architect, Business analyst, User representative, Business process owner
|  |  | System requirements |  | IT-architect, Business analyst, User representative, Business process owner
|  |  | Detailed study |  | IT-architect, Business analyst, User representative, Developer
|  |  | System architecture |  | IT-architect, Operations manager, Developer
Procurement
|  | Evaluate tenders |  | Project manager
|  |  | Evaluation report |  | Project manager
|  |  | Minutes |  | Project manager
|  | Issue a call for tenders |  | Project manager
|  |  | Tender documentation |  | Project manager
|  |  | Offer |  | Project manager, Operations manager, Developer
|  | Prepare a call for tenders |  | Project manager
|  |  | Tender documentation |  | Project manager
|  | Draw up a procurement plan |  | Project manager
|  |  | Project management plan |  | Project manager
|  | Decide on contract award |  | Project sponsor
|  |  | Publication |  | Project sponsor, Project manager
|  |  | Checklist |  | Project sponsor, Project manager
|  |  | Project decision steering |  | Project sponsor, Project manager, Project committee member, Quality and risk manager
|  | Decide on call for tenders |  | Project sponsor
|  |  | Checklist |  | Project sponsor, Project manager
|  |  | Project decision steering |  | Project sponsor, Project manager, Project committee member, Quality and risk manager
|  | Draw up agreement |  | Project manager
|  |  | Agreement |  | Project manager, Project sponsor
Deployment organization
|  | Design a deployment concept |  | Project manager
|  |  | Deployment concept |  | Project manager, Business analyst, User representative, Business process owner
Testing
|  | Design a test concept |  | Test manager
|  |  | Test concept |  | Test manager, Tester, Operations manager, Business analyst, Developer
IT migration
|  | Design a migration concept |  | IT-architect
|  |  | Migration concept |  | IT-architect, Business analyst, Developer
IT operation
|  | Design an operating concept |  | Operations manager
|  |  | Operating concept |  | Operations manager, Application owner, IT-architect
|  |  | Agreement |  | Operations manager, Project sponsor, Project manager
Information security and data protection
|  | Decide on ISDP concept |  | Project manager
|  |  | Checklist |  | Project manager
|  |  | Project decision management & execution |  | Project manager, Quality and risk manager
|  | Design ISDP concept |  | ISDP manager
|  |  | ISDP concept |  | ISDP manager, Operations manager, Application owner, IT-architect
IMPLEMENTATION
Project steering
|  | Decide on phase release |  | Project sponsor
|  |  | Checklist |  | Project sponsor, Project manager
|  |  | QA and risk report |  | Project sponsor, Quality and risk manager
|  |  | Project decision steering |  | Project sponsor, Project manager, Project committee member, Quality and risk manager
|  | Steer project |  | Project sponsor
|  |  | QA and risk report |  | Project sponsor, Quality and risk manager
|  |  | Project decision steering |  | Project sponsor, Project manager, Project committee member, Quality and risk manager
Project management
|  | Lead change management |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Change request |  | Project manager, Business analyst, User representative
|  |  | Change status list |  | Project manager
|  | Agree on and steer goods/services |  | Project manager
|  |  | Quote request |  | Project manager
|  |  | Evaluation report |  | Project manager
|  |  | Agreement |  | Project manager, Project sponsor
|  | Prepare phase release |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Project status report |  | Project manager
|  |  | Phase report |  | Project manager
|  | Deal with problems and benefit from experience |  | Project manager
|  |  | Lessons learned |  | Project manager
|  | Manage and control project |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Work order |  | Project manager
|  |  | Project status report |  | Project manager
|  |  | Minutes |  | Project manager
|  | Perform quality assurance |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Review report |  | Project manager
|  | Manage risks |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Project status report |  | Project manager
|  | Manage stakeholders and communication |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Stakeholder list |  | Project manager, Project sponsor, Business analyst, Business process owner
|  |  | Stakeholder Interests |  | Project manager
Agile development
|  | Keep a product backlog |  | Project manager
|  |  | Product backlog |  | Project manager, Business analyst, Developer
|  | Design release plan |  | Developer
|  |  | Release plan |  | Developer, Operations manager, Business analyst
|  | Conduct sprints |  | Developer
|  |  | Sprint backlog |  | Developer, Business analyst
|  |  | Increment |  | Developer
|  |  | Minutes |  | Developer, Project manager
Business organization
|  | Realize business organization |  | Business analyst
|  |  | Process description |  | Business analyst, User representative, Business process owner
|  |  | Organization description |  | Business analyst, User representative, Business process owner
|  |  | Organization implemented |  | Business analyst, Business process owner
IT system
|  | Realize prototype |  | Developer
|  |  | Prototype realized |  | Developer, IT-architect
|  |  | Prototype documentation |  | Developer, IT-architect
|  | Realize system |  | Developer
|  |  | System developed or parameterized |  | Developer
|  |  | System architecture |  | Developer, Operations manager
|  |  | User manual |  | Developer, User representative
|  |  | Detailed specifications |  | Developer, Business analyst, IT-architect
|  | Prepare system integration |  | Developer
|  |  | Interfaces realized |  | Developer
|  |  | System architecture |  | Developer, Operations manager
|  |  | Integration and installation instructions |  | Developer, Operations manager
|  |  | Detailed specifications |  | Developer, Business analyst, IT-architect
Deployment organization
|  | Prepare deployment |  | Project manager
|  |  | Deployment measures and organization realized |  | Project manager, Business analyst, Business process owner
|  | Decide on preliminary acceptance |  | Project manager
|  |  | Acceptance report |  | Project manager, Operations manager, User representative, Application owner, Developer, Quality and risk manager
|  |  | Checklist |  | Project manager
|  |  | Project decision management & execution |  | Project manager, Quality and risk manager
Testing
|  | Conduct test |  | Test manager
|  |  | Test report |  | Test manager, Tester
|  |  | Test concept |  | Test manager, Tester, Operations manager, Business analyst, Developer
|  | Realize test infrastructure |  | Operations manager
|  |  | Test system |  | Operations manager, Test manager
|  |  | Test data |  | Operations manager, Business analyst, Test manager
IT migration
|  | Realize migration procedure |  | Developer
|  |  | Detailed specifications |  | Developer, Business analyst, IT-architect
|  |  | Migration procedure |  | Developer, Operations manager
IT operation
|  | Realize operation |  | Operations manager
|  |  | Operating infrastructure realized |  | Operations manager
|  |  | Operating manual |  | Operations manager
|  |  | Operating organization realized |  | Operations manager, Application owner
|  | Integrate system in operation |  | Operations manager
|  |  | Operating manual |  | Operations manager
|  |  | System integrated |  | Operations manager, Developer
Information security and data protection
|  | Implement ISDP concept |  | Project manager
|  |  | ISDP measures |  | Project manager, Operations manager, ISDP manager, Developer
|  |  | ISDP concept |  | Project manager, Operations manager, Application owner, IT-architect
DEPLOYMENT
Project steering
|  | Decide on project closure |  | Project sponsor
|  |  | QA and risk report |  | Project sponsor, Quality and risk manager
|  |  | Checklist |  | Project sponsor, Project manager
|  |  | Project decision steering |  | Project sponsor, Project manager, Project committee member, Quality and risk manager
|  | Steer project |  | Project sponsor
|  |  | QA and risk report |  | Project sponsor, Quality and risk manager
|  |  | Project decision steering |  | Project sponsor, Project manager, Project committee member, Quality and risk manager
Project management
|  | Lead change management |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Change request |  | Project manager, Business analyst, User representative
|  |  | Change status list |  | Project manager
|  | Agree on and steer goods/services |  | Project manager
|  |  | Quote request |  | Project manager
|  |  | Evaluation report |  | Project manager
|  |  | Agreement |  | Project manager, Project sponsor
|  | Deal with problems and benefit from experience |  | Project manager
|  |  | Lessons learned |  | Project manager
|  | Manage and control project |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Work order |  | Project manager
|  |  | Project status report |  | Project manager
|  |  | Minutes |  | Project manager
|  | Prepare project closure |  | Project manager
|  |  | Lessons learned |  | Project manager
|  |  | Final project evaluation |  | Project manager
|  | Perform quality assurance |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Review report |  | Project manager
|  | Manage risks |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Project status report |  | Project manager
|  | Manage stakeholders and communication |  | Project manager
|  |  | Project management plan |  | Project manager
|  |  | Stakeholder list |  | Project manager, Project sponsor, Business analyst, Business process owner
|  |  | Stakeholder Interests |  | Project manager
Agile development
|  | Keep a product backlog |  | Project manager
|  |  | Product backlog |  | Project manager, Business analyst, Developer
|  | Design release plan |  | Developer
|  |  | Release plan |  | Developer, Operations manager, Business analyst
|  | Conduct sprints |  | Developer
|  |  | Sprint backlog |  | Developer, Business analyst
|  |  | Increment |  | Developer
|  |  | Minutes |  | Developer, Project manager
Business organization
|  | Activate business organization |  | Business analyst
|  |  | Business organization activated |  | Business analyst, User representative, Business process owner
IT system
|  | Activate system |  | Developer
|  |  | System activated |  | Developer, Operations manager, Business analyst, Application owner
Deployment organization
|  | Execute deployment |  | Project manager
|  |  | Deployment measures carried out |  | Project manager, Business analyst, Business process owner
|  | Decide on acceptance |  | Project manager
|  |  | Acceptance report |  | Project manager, Operations manager, User representative, Application owner, Developer, Quality and risk manager
|  |  | Checklist |  | Project manager
|  |  | Project decision management & execution |  | Project manager, Quality and risk manager
|  | Decide on launch of operation |  | Project sponsor
|  |  | Checklist |  | Project sponsor, Project manager
|  |  | Project decision steering |  | Project sponsor, Project manager, Project committee member, Quality and risk manager
Testing
|  | Conduct test |  | Test manager
|  |  | Test report |  | Test manager, Tester
|  |  | Test concept |  | Test manager, Tester, Operations manager, Business analyst, Developer
|  | Transfer test concept and infrastructure |  | Test manager
|  |  | Minutes |  | Test manager, Project manager
IT migration
|  | Decommission the legacy system |  | IT-architect
|  |  | Legacy system decommissioned |  | IT-architect, Operations manager, Business analyst
|  | Decide on acceptance of migration |  | Project manager
|  |  | Acceptance report |  | Project manager, Operations manager, User representative, Application owner, Developer, Quality and risk manager
|  |  | Checklist |  | Project manager
|  |  | Project decision management & execution |  | Project manager, Quality and risk manager
|  | Conduct migration |  | Developer
|  |  | Migration carried out |  | Developer, Operations manager, Business analyst, Application owner
IT operation
|  | Activate operation |  | Operations manager
|  |  | Operating manual |  | Operations manager
|  |  | Operation activated |  | Operations manager, Application owner, Developer
Information security and data protection
|  | Transfer ISDP concept |  | ISDP manager
|  |  | ISDP concept |  | ISDP manager, Operations manager, Application owner, IT-architect
|  |  | Checklist |  | ISDP manager, Project manager